## Zoho Desk 30-Day Plan
Phase | Day Range | Task Category | Detailed Activity | Start Date | End Date | Status | Remarks
Phase 1 | Day 1–2 | Planning | Define service desk objectives, scope (internal/customer), and success criteria |  |  | Not Started
Phase 1 | Day 3–4 | Planning | Identify support channels, support hours, escalation matrix, and stakeholders |  |  | Not Started
Phase 1 | Day 5 | Design | Finalize ticket categories, subcategories, priority matrix, and SLAs |  |  | Not Started
Phase 2 | Day 6–7 | Configuration | Create Zoho Desk departments, roles, agents, and permissions |  |  | Not Started
Phase 2 | Day 8–9 | Configuration | Configure ticket statuses, business hours, holidays, and email channels |  |  | Not Started
Phase 2 | Day 10–12 | Automation | Set up assignment rules, SLA policies, escalation rules, and notifications |  |  | Not Started
Phase 3 | Day 13–15 | Knowledge Base | Identify top recurring issues and draft 10–20 knowledge base articles |  |  | Not Started
Phase 3 | Day 16–18 | Self-Service | Configure help center, branding, categories, and KB visibility rules |  |  | Not Started
Phase 4 | Day 19–21 | Integration | Integrate email, Teams/Slack, CRM, and enable SSO if required |  |  | Not Started
Phase 4 | Day 22–24 | Reporting | Create dashboards for SLA, FCR, backlog, and category trends |  |  | Not Started
Phase 5 | Day 25–26 | Testing | Perform UAT, simulate P1/P2 incidents, SLA breach and escalation scenarios |  |  | Not Started
Phase 5 | Day 27–28 | Training | Conduct agent training, SOP walkthrough, and ticket handling best practices |  |  | Not Started
Phase 5 | Day 29 | Go‑Live Prep | Finalize email routing, portal access, and escalation contacts |  |  | Not Started
Phase 5 | Day 30 | Go‑Live | Official go‑live and hypercare support |  |  | Not Started